## User Stories
US# | Title | As a/an | I want to… | so that… | Priority | Time Estimate in Person/days | Person/Days required to get work done (Velocity inc.) | Iteration
1 | Librarian log in/ log out | librarian | log in and log out to the system | I can access features only available to librarians and secure all access | 1 | 1 | 5 | 1
2 | CRUD Material | librarian | create/update/delete new or existing material to the materials catalog | I can add newly purchased material, remove material and edit to keep it up to date/correct errors | 3 | 0.5 | 2.5 | 1
3 | CRUD Patrons | librarian | create/update/delete new or existing patrons to the patrons database | I can have new users check out material, remove patrons and keep all information about them up to date | 4 | 0.5 | 2.5 | 1
26 | Overdue report | librarian | see all overdue material | I can keep track of checked out material | 11 | 0.5 | 2.5 | 1
25 | Fine overview | librarian | view all outstanding fines | I can keep track of all overdue items | 26 | 0.5 | 2.5 | 2
5 | Collect fines | librarian | accept and proccess payements | I can keep track of all fees for overdue material | 26 | 0.5 | 2.5 | 2
23 | Check in materials | librarian | be able to check in rented material | I can accept returned items from patrons | 6 | 1 | 5 | 1
22 | Search material | librarian | search through all inventory | I can check for availability | 7 | 0.5 | 2.5 | 1
21 | Check out material | librarian | be able to check out materials to patrons | I can keep track of all material checked out | 5 | 1 | 5 | 1
8 | Authorize access rights and edit Librarians | super-Librarian | allow different access rights to different user groups and CRUD librarians | I can keep track of the granted rights of all user groups and control librarians | 31 | 1 | 5 | 2
9 | Administrative rights | super-librarian | have the same rights and priviliges of all sub users in the system | I can have ultimate authority and control within the system | 32 | 1 | 5 | 2
13 | Search material | patron | search through the material databse | I can check the inventory of the library and its availability | 24 | 0.5 | 2.5 | 1
20 | Checkout history | patron | see all material currently checked out | I can keep track of the matrial that I have checked out | 23 | 0.5 | 2.5 | 2
14 | Fine payment | patron | see and pay fines online | I can pay without going to the library | 26 | 1 | 5 | 2
19 | Wishlist | patron | add and delete items to a personal wishlist | I can keep track of the material I want to check out in the future | 27 | 1 | 5 | 2
15 | Reserve material | patron | make a reservation | I can reserve material to pick up later | 25 | 1 | 5 | 2
17 | Search databae | guest | browse materials and check for availiblity | I see what items are in the library | 9 | 1 | 5 | 1
28 | Search Patrons | librarian | search through all patrons in the system | I can see who is a registered patron and view their information | 8 | 0.5 | 2.5 | 1
29 | Patron Login/ Logout | patron | login and log out of the system | I can access the system | 20 | 1 | 5 | 1
30 | Patron View | patron | see my personal information in the system | view my address, email and phone number | 21 | 0.5 | 2.5 | 1
31 | Super-Librarian Login/Logout | super-Librarian | login and log out of the system | I can access the whole system with universal rights | 30 | 1 | 5 | 2
32 | Mobile Device | patron | have access from my mobile device | I can access the system with a tablet or a phone on the way | 12 | 2 | 10 | 1
Time estimate for the overall project | [5 empty] | 18 | 90 | ÷3 workers= | 30
Working days remaining- starting March 25 | [5 empty] | 32
Expected Completion Date | [5 empty] | May 7, 2013
As of right now, the expected completion date is slightly ahead the customer deadline.
To avoid penalties in form of point deductions the time estimations and velocity were fitted to the customer deadline and may vary a lot over time.
In this time estimate we calculate with a 20% Productivity, due to other jobs outstanding as students.
Velocity and time estimations are subject to change when Iteration 1 starts or customer requirements change.
[5 empty] | Person-hours of work: | 3.5
[5 empty] | Assuming 70% velocity, the hours it will take to actually complete the work: | 5
|  |  |  | Hours of work (including 70% velocity) that can be completed by a 4 person team in 1 iteration: | 448
|  |  |  | Hours of work (including 70% velocity) that can be completed by a 3 person team in 1 iteration: | 336

## Dictionary
SLPL Information System Dictionary
| Term | Definition
1 | Librarian
2 | Super Librarian
3 | Public
4 | Patron
5
6
7
8
9
10
11

## Business Rules
SLPL Information System Business Rules
| BR-1 | Only librarians are allowed to add, modify, and delete materials in the materials database.
| BR-2 | You should be able to search materials by author and title without being required to login.

## Technical Requirements
SLPL Information System Technical Requirements
* Indicates the BR will not be implemented for this project, but serves as an example for future projects.
| TR-1 | The system shall fully operate with current versions of Microsoft Internet Explorer, Firefox, and Google Chrome as well as standard Android and IOS browsers.
| TR-2 | The system shall fully operate on a corporate approved, Microsoft Windows 200? server using Internet Information Server ?. (instruct.biz.uiowa.edu)
| * TR-3 | The system shall accommodate 100 concurrent users at peak usage times of 9AM – 4PM, local time.
| * TR-4 | All pages generated by the system shall be fully downloadable in no more than 10 seconds over a 512kbsp DSL connection.
| TR-5 | Responses to queries shall take no longer than 7 seconds to load onto the screen after the users submits the query.

## Constraints
SLPL Information System Constraints
* Indicates the CO will not be implemented for this project, but serves as an example for future projects.
| * CO-1 | All network transactions that involve logins, financial information, or personally identifiable information shall be encrypted.
| * CO-2 | The system shall provide an online hierarchical cross-linked help system in HTML that describes, illustrates, and provides examples for all system functions.
| CO-3 | All HTML code shall conform to XHTML 1.0 transitional.
| CO-4 | All CSS code shall conform to CSS 2.1.